## Slide 1: Coordinated Resource Management Planning (CRMP)
Who, What, Where, Why, When ??
So What ??

## Slide 2
The Role of a Coordinated Resource Management Plan
Coordinated Resource Management and Planning (CRMP) is a resource planning, problem solving, and management (decision making) process that allows for direct participation of everyone (stakeholders) concerned with resource management in a given planning area.
The concept underlying CRMP is that coordinating resource uses results in improved resource management and minimizes conflict among land users, landowners, government agencies, and interest groups.
Resource problems are addressed and solved based on resource boundaries; they are not constrained by individual, agency, or political boundary.
The CRMP process operates on the local level with the underlying philosophy being that those who live, work, and recreate on a given piece of land are the people most interested in and capable of developing plans for its use.
Inevitable conflicts in resource use that arise from diverse interest and goals are best solved by face-to-face communication among all interested groups and individuals. Experience has shown that people with diverse viewpoints who voluntarily meet together as a planning team will find common ground as they interact with one another and have a chance to observe resource problems first hand. Through discussion, landowners, users, and resource managers begin to understand and respect each other's viewpoints. The end result is constructive problem solving through cooperative resource planning.
The local focus of the CRMP process makes community support essential. Community awareness of the constructive, problem solving nature of the plan strengthens the commitment of those involved in the planning group to make the plan work. In addition, news of the successful implementation of the CRMP process in an area can stimulate surrounding areas to follow suit, reducing resource conflicts throughout a region.

## Slide 3
Goals: Example
Develop and Implement a coordinated resource management plan for the recovery of the fisheries and economies of the South Fork Trinity River Basin.
Promote equality, cooperation and voluntary participation among all members of the CRMP process.
Build trust.
Objectives:
Provide the leadership necessary to bring diverse interest groups to agreement
on resource management opportunities.
Perform upland watershed analysis and inventory.
Determine risk potential for sediment yield from private and public land.
Assess water quality and quantity improvement opportunity.
Strive to prevent listing of species under the Endangered Species Act through habitat improvement and population recovery.
Increase forest productivity through soil conservation.
Provide access to, and facilitate transfer of, technical information and expertise.
Serve as a liaison between the agencies, industries and local grass roots groups.

## Slide 4: CRMP FLOW CHART
CRMP Request from private or public entity.
Private and public landowners and managers, resources managers and others in the general planning area invited to initial meeting.
Define specific planning area; list issues, problems and concerns; list objectives. Determine information available and needed, including maps and resource data. List all problems on one sheet and all objectives on a separate sheet.
Use checklist to make sure all resources have been considered.
List each objective on a separate sheet. List all actions needed to accomplish it. Use checklist to make sure all resources have been considered.
For each action, list the who, what, when and how long information; organize it into a logical sequence to meet the objective.
Make CRM decision.
Reevaluate the plan to determine if it will really solve the problems listed. Set up a system to maintain actions.
Implement the plan
Schedule annual reviews of progress, accomplishments, problems, new objectives and lay
out the coming year’s work.

## Slide 5: FOUR STEPS IMPORTANT TO A SUCESSFUL CRM
1. The local private landowners must recognize that there is a need and have the desire to fix that need. The private landowner must be willing to commit the time, and resources to arrive at solution to fix that need and be willing to work with the other land managers in implementing practices identified by group consensus.

## Slide 6: FOUR STEPS CONTINUED
2. Everyone seated at the table must be a manager of the resource and must be able to make decisions for the agency or land owner they represent. It is the duty of the facilitator to make sure that only resource managers are seated at the table. Interested groups may attend the meetings and may voice opinions at the appropriate place when questioned or during public comment periods.

## Slide 7: FOUR STEPS CONTINUED
2. (continued) The facilitator must also make sure that there is only one voice for each resource management group. Some agencies will send more than one person to the meetings, but only one may sit at the table as a representative of that agency.
3. It is important to remember that special interest groups (Rocky Mountain Elk Foundation, Mule Deer Foundation, and others…..) are not decision makers unless they own land with the boundaries of the CRM

## Slide 8: FOUR STEPS CONTINUED
3. (continued) It is important to give special interest groups a chance to comment and to feel that their opinions are respected because often they can and do help with financing the resource improvements.
4. It is important that the facilitator makes the agenda and that there is a time limit on each item. Often position gets in the way of need and consensus cannot be reached at this meeting.